## DevLog
Vanam Mk-1 SSMPLV Development Log
Expected DoL: 07-06-2025
Date | Activity
2025-03-07 | First Team Meeting
2025-03-08 | Team Splitting
2025-03-10 | E9-3 Rocker Motors bought
2025-03-11 | First batch of components bought
2025-03-13 | Test date for avionics and parachute tests confirmed
2025-03-18 | First batch of components arrived
2025-03-18 | Finished making Flight Hardware V0.5
2025-03-19 | Finished flight-code V0.5
2025-03-20 | Avionics and parachute test I
2025-03-22 | Flight Computer V1 gerbers sent for PCB production
2025-03-22 | Test date for avionics and parachute test II confirmed